Hire'in Solutions

Final SOP Launch & Process Implementation Playbook

Successive rollout plan, missing-domain SOP library, training linkage, governance workflow, and platform adoption standards

| Field | Details |
| --- | --- |
| Document Status | Leadership Release Draft - Version 1.0 |
| Prepared For | Hire'in Solutions Leadership, Ops, HR, TA Delivery, Sales, Marketing, Finance and Development |
| Prepared By | CEO / Founder Office with BA, TA Delivery, BD and CMO operating lens |
| Effective Intent | Roll out SOPs in controlled waves without overwhelming the team |
| Date | June 29, 2026 |

Owner Decision This document is intended to be approved centrally and launched in waves. Managers may provide operational feedback, but the rollout should not wait on an open-ended review cycle. The goal is adoption, training, behavior change and measurable execution - not paperwork.

# 1. Executive Summary

Hire'in Solutions is moving from informal process knowledge into a structured operating system. The purpose is not to create paperwork or slow recruiters down. The purpose is to remove staffing chaos, improve requirement understanding, protect candidate trust, increase submission quality, support compliance, and give managers clear execution standards.

This playbook provides the final SOP library, including the missing domains identified during leadership discussion: Marketing, Engineering and Professional Services, Legal and Compliance, Finance and Billing, Business Development, Candidate Experience, AI-driven Requirement Synthesis, and Independent SaaS Platform Usage for KleriQ.ai and ProKred.com.

Rollout Philosophy Launch the SOPs in succession. Start with the minimum set that protects delivery, tools, data, and submission quality. Then layer in candidate experience, platform adoption, marketing, business development, finance, legal, and advanced domains. Team members should understand why each SOP matters before they are expected to fully follow it.

# 2. What Hire'in Is Built On

Hire'in should not be positioned as just another staffing company. The core operating promise is to bring clarity, trust and disciplined execution to staffing. Hire'in uses technology and structured delivery standards to convert fragmented hiring demand into aligned execution and to convert candidate readiness into compliant, submission-ready delivery.

| Core Value | How It Shows Up in Daily Work |
| --- | --- |
| Candidate-first delivery | Candidates are not inventory. Every candidate should receive respectful, honest and timely communication. This is especially important in healthcare where career decisions are emotional and deeply personal. |
| Communication clarity | Hire'in exists to reduce chaos between corporate hiring teams, recruiters, candidates, MSP/VMS partners and internal delivery teams. Requirements, rates, candidate status and next steps should be clear and documented. |
| Speed with quality | Fast sourcing is not enough. Speed must be paired with intake discipline, screening, quality control and submission readiness. |
| AI with human judgment | AI-driven tools support synthesis, prioritization and productivity. Final responsibility for accuracy, ethics, compliance, candidate treatment and client communication remains with trained humans. |
| Candidate digital safety | Candidate documents, IDs, credentials, work authorization records, licenses and personal information must be handled through approved secure channels and never casually shared. |
| Process transparency | If work is not visible in ATS, workflow, dashboards, approved tools or audit logs, it is not operationally reliable. |
| Ownership mindset | Team members should think like operators, not task workers. They should identify blockers, protect company trust, recommend improvements and escalate early. |
| Metrics before opinions | Performance should be evaluated through activity, quality, conversion, compliance, aging, audit scores, margin and start outcomes. |
| Long-term partnership | Hire'in should build relationships before, during and after placements with candidates, clients, partners and internal teams. |
| Confidentiality by default | Client information, rates, candidate data, tool credentials, internal strategy and commercial terms must remain confidential unless approved for sharing. |

# 3. Hire'in Mission and Operating Positioning

Recommended mission statement for internal rollout:

Mission Statement Hire'in brings clarity, trust and execution discipline to staffing. We help companies convert hiring uncertainty into clear requirements, aligned delivery, transparent candidate communication, secure document workflows, and faster role fulfillment.

| Positioning Pillar | Meaning | Connected SOPs |
| --- | --- | --- |
| Requirement clarity | Every role must be understood before recruiters spend time sourcing. | REQ-001, TA-001, SALES-001 |
| Candidate trust | Candidates should know what role they are being considered for, what documents are requested, and how their information will be handled. | CX-001, HC-001, PLAT-001 |
| Submission readiness | A candidate is not ready until their profile, screening, notes, documents and submission package meet the role requirements. | TA-003, HC-001, IT-001, ENG-001 |
| Operational control | Tools, access, workflows, reviews, audits and KPIs should be controlled through the system. | GOV-001, OPS-001, HR-001, AUDIT-001 |
| Growth engine | Marketing, BD, sales and delivery must work together to generate demand and convert it into results. | MKT-001, BD-001, SALES-001, FIN-001 |

# 4. Final SOP Library - Including Missing Domains

The final library should include 21 SOPs. These should not all be launched at once. They should be seeded into the app and rolled out in waves.

| Code | Title | Category | Purpose |
| --- | --- | --- | --- |
| HIS-SOP-GOV-001 | SOP Governance, Document Control & Change Management | General / Governance | Controls ownership, approval, versioning, review cadence and publishing. |
| HIS-SOP-REQ-001 | AI-Driven Requirement Synthesis, Hiring Manager Alignment & Execution Brief | Requirement Clarity | Uses KleriQ-style requirement synthesis to standardize job understanding before sourcing. |
| HIS-SOP-TA-001 | Requisition Intake, Rate Alignment & Delivery Kickoff | TA Delivery | Ensures no recruiter starts sourcing without role, rate, pay, margin and must-have clarity. |
| HIS-SOP-TA-002 | Sourcing, Outreach, Candidate Ownership & Consent | TA Delivery | Controls sourcing, candidate ownership, duplicate handling, outreach quality and consent/RTR. |
| HIS-SOP-TA-003 | Screening, Qualification & Submission QC | TA Delivery | Defines screening quality gates and submission readiness checks. |
| HIS-SOP-TA-004 | Interview, Offer, Start & Retention Follow-Through | TA Delivery | Controls interview coordination, offer follow-up, start confirmation and post-start check-ins. |
| HIS-SOP-HC-001 | Healthcare Credential Packet & Compliance Readiness | Healthcare | Defines healthcare credential awareness, document collection, packet completeness and compliance readiness. |
| HIS-SOP-IT-001 | IT Staffing Delivery, Technical Screening & Submission Governance | IT Staffing | Defines IT requirements, technical screening, resume fit and submission governance. |
| HIS-SOP-ENG-001 | Engineering & Professional Services Delivery Standards | Engineering / Professional Services | Adds delivery standards for engineering, professional services and specialized business roles. |
| HIS-SOP-SALES-001 | Client, MSP/VMS, Rate Governance & Escalation | Sales / Account Management | Controls client intake, rate/margin guardrails, MSP/VMS communication and escalation. |
| HIS-SOP-BD-001 | New Client Acquisition, Proposals, RFPs & Client Onboarding | Business Development | Defines prospecting, proposal, RFP response, client onboarding and handoff to delivery. |
| HIS-SOP-MKT-001 | Employer Brand, Digital Marketing & Lead Generation | Marketing | Defines content, employer brand, candidate attraction, LinkedIn/social, insights and campaign workflows. |
| HIS-SOP-CX-001 | Candidate Experience, Communication SLA & Re-Engagement | Candidate Experience | Sets candidate communication SLA, rejection handling, placement follow-up, re-engagement and NPS/feedback. |
| HIS-SOP-PLAT-001 | Independent SaaS Platform Usage - KleriQ.ai and ProKred.com | Platform / Partner Tools | Explains that KleriQ and ProKred are separate SaaS platforms used by Hire'in as pilot/design tools, not internal-only systems. |
| HIS-SOP-LEGAL-001 | Contracts, Data Privacy, EEOC & Immigration Compliance | Legal / Compliance | Covers NDA/contract handling, data privacy, job-related selection criteria, visa/work authorization documentation and escalation. |
| HIS-SOP-FIN-001 | Invoicing, Contractor Payroll, AR/AP & Margin Governance | Finance / Billing | Controls timesheets, invoicing, billing, payroll, margin integrity, AR/AP and payment follow-up. |
| HIS-SOP-OPS-001 | Tool Access, Credential Control & Deprovisioning | Operations / Security | Controls approved access requests, least privilege, password resets, exits and access removal. |
| HIS-SOP-HR-001 | Training, Acknowledgment, Goals & Performance Linkage | HR / People Operations | Maps SOPs to training, acknowledgments, role goals, coaching and PIP linkage. |
| HIS-SOP-AUDIT-001 | KPI Dashboard, Weekly Audit & Monthly Business Review | Management / Audit | Defines weekly audits, KPI cadence, MBR structure and corrective-action tracking. |
| HIS-TRAIN-001 | Role-Based Training Curriculum & Certification Plan | Training | Defines role-based training tracks, quizzes, work samples and certification. |
| HIS-TPL-001 | Manager Acknowledgment, Audit Checklists & Field Templates | Templates | Provides manager templates, checklists and field tools to execute SOPs consistently. |

# 5. Why the Missing SOPs Matter

| Missing Domain | Why It Matters | Business Value |
| --- | --- | --- |
| Marketing | Top staffing firms use marketing to create candidate trust, client credibility and recruiter enablement. | Improves lead generation, content authority, candidate attraction and brand consistency. |
| Engineering & Professional Services | Hire'in positioning includes more than Healthcare and IT. Delivery standards must exist for each served vertical. | Prevents recruiters from using healthcare/IT logic for unrelated professional roles. |
| Legal & Compliance | Staffing touches data privacy, contracts, candidate consent, selection criteria, work authorization and confidentiality. | Reduces risk and improves client confidence. |
| Finance & Billing | Timesheets, invoicing, payroll, AR/AP and margin controls directly affect cash flow and trust. | Protects margin, reduces billing disputes and improves collections. |
| Business Development | Existing client/MSP management is different from new client acquisition. | Improves new client acquisition, proposals, RFPs and smooth client onboarding. |
| Candidate Experience | Candidate communication is a brand asset and a conversion driver. | Improves show-up, interview readiness, redeployment and referral quality. |
| Requirement Synthesis | Poor requirement understanding is one of the biggest causes of wasted sourcing. | Aligns hiring intent, recruiter execution and candidate pitch. |
| Platform Usage | KleriQ and ProKred are separate SaaS platforms. Employees need correct positioning and boundaries. | Prevents confusion, improves adoption and protects commercial positioning. |

# 6. KleriQ.ai and ProKred.com Usage Standard

KleriQ.ai and ProKred.com should be explained to the team as independent third-party SaaS platforms built within the same founder ecosystem and used by Hire'in as pilot/design-partner tools. They are not internal-only tools and should be positioned carefully.

| Platform | Role in Hire'in Execution | Employee Message |
| --- | --- | --- |
| KleriQ.ai | Requirement clarity and communication standardization. Helps convert job descriptions, client notes, VMS details and hiring manager expectations into a unified execution brief. | Use KleriQ to understand the role better, not to replace recruiter judgment. |
| ProKred.com | Secure candidate-side credential/document profile and submission packet workflow. Helps candidates collect, manage, share and track documentation with visibility. | Explain ProKred as a secure candidate-friendly SaaS platform, not as a forced internal Hire'in form. |

Important Candidate-Side Message for ProKred ProKred has a candidate-side value proposition. Candidates can use it to maintain a reusable profile, track document readiness, manage credentials, and reduce repeated document sharing. Recruiters may introduce it as a secure, candidate-friendly platform that supports faster and more organized submissions. Recruiters must not claim that ProKred is mandatory unless the specific workflow or client/program requires it and this has been approved by management.

| Do | Do Not |
| --- | --- |
| Say: ProKred helps you securely organize and share your credential documents for submission readiness. | Do not say: This is only Hire'in's internal tool. |
| Say: You can use ProKred to make future submissions easier and more visible. | Do not force candidates to upload documents without clear consent. |
| Say: KleriQ helps our delivery team clarify requirements and reduce mismatch. | Do not tell clients/candidates AI makes final decisions. |
| Keep ProKred and KleriQ branding separate from Hire'in branding when explaining SaaS value. | Do not represent Hire'in as owning candidate data inside third-party SaaS without proper terms. |
| Use approved scripts and FAQs only. | Do not improvise privacy, legal or security claims. |

# 7. Successive Rollout Plan - Avoid Overwhelming the Team

The team should not receive all SOPs in one meeting. Each wave should answer three questions: why it matters, what changes tomorrow, and how success will be measured.

| Wave | Timing | Audience | SOPs | Purpose | Enforcement |
| --- | --- | --- | --- | --- | --- |
| Wave 0 - Leadership Alignment | Week 0 | CEO, Ops, HR, Department Heads | GOV-001, HR-001, AUDIT-001 | Approve rollout model, assign SOP owners, seed app library, decide enforcement dates. | No team-wide enforcement yet. |
| Wave 1 - Delivery Control Foundation | Weeks 1-2 | TA, Healthcare, IT, Sales, Ops | REQ-001, TA-001, TA-003, OPS-001, SALES-001 | Stop sourcing chaos: intake clarity, rate alignment, submission QC, approved tool access. | Soft enforcement with coaching. |
| Wave 2 - Candidate & Submission Experience | Weeks 3-4 | Recruiters, Leads, Healthcare, IT, Candidate-facing teams | TA-002, TA-004, HC-001, CX-001, PLAT-001 | Improve candidate communication, ProKred adoption, credential readiness, interview-to-start follow-through. | Start measured audits. |
| Wave 3 - Growth, Marketing & BD | Weeks 5-6 | Marketing, Sales, BD, Managers | MKT-001, BD-001, ENG-001 | Create consistent market message, content engine, lead generation and vertical delivery standards. | Role-based implementation only. |
| Wave 4 - Finance, Legal & Operating Maturity | Weeks 7-8 | Finance, Ops, HR, Sales, Managers | LEGAL-001, FIN-001, TRAIN-001, TPL-001 | Control billing, contracts, data privacy, compliance, training records and manager templates. | Full audit readiness. |
| Wave 5 - Full Integration & MBR | Weeks 9-12 | Leadership and all managers | All active SOPs | Connect SOP adoption to KPIs, role scorecards, audits and monthly business review. | Full enforcement begins. |

# 8. Team Training Cadence

| Rule | Standard |
| --- | --- |
| Do not launch more than two operational SOPs per week | Team members need time to understand and apply each process. |
| Each SOP launch should be 30-45 minutes | Keep training practical: purpose, process, examples, do/don't, checklist, KPI. |
| Use role-based training | Recruiters do not need deep Finance training; Finance does not need deep sourcing training. |
| Require acknowledgment only after training | Do not ask employees to acknowledge documents they have not been trained on. |
| Use live work samples | Certification should include one real intake, one real candidate screen, one real packet, or one real audit sample. |
| Refresh after 30-45 days | Update Version 1.1 based on actual adoption gaps, not abstract opinions. |

# 9. App-Based SOP Governance and Review Workflow

The SOPs should be managed inside the existing app using the central review, discussion and approval workflow service already available across other features. Do not duplicate workflow logic.

Developer Rule Build SOP governance as a new entity type on the central WorkflowService. The app should support entityType = SOP and entityId = sopDocumentId. Review, comments, approval, due dates, audit logs and notifications should reuse the existing workflow service.

| Lifecycle Status | Meaning |
| --- | --- |
| DRAFT | SOP is being drafted or revised. |
| IN_REVIEW | Reviewers have been assigned. |
| CHANGES_REQUESTED | Reviewers requested required change. |
| APPROVED | Approver has approved the SOP. |
| PUBLISHED | SOP is published to the library. |
| TRAINING_ASSIGNED | Training assigned to impacted roles. |
| ACKNOWLEDGED | Employees acknowledged assigned SOP version. |
| ACTIVE | SOP is enforceable. |
| UNDER_REVISION | Active SOP is being updated. |
| RETIRED | SOP is no longer active. |

| Reviewer Action | Meaning |
| --- | --- |
| Comment | General feedback or clarification. |
| Mark Reviewed | Reviewer has no blocker. |
| Approve | Reviewer approves the SOP. |
| Approve with Comments | SOP can proceed; comments may be handled in future version. |
| Request Changes | Must be corrected before publish. |
| Reject | Major issue requiring CEO/Ops decision. |
| No Response / No Objection | Reviewer did not respond by due date; CEO may proceed. |

# 10. Development Requirements Summary

| Build Area | Requirement |
| --- | --- |
| SOP Library | Create searchable library by code, title, category, owner, status, version and effective date. |
| SOP Version Control | Published versions are locked; edits create a new version. |
| Central Workflow Reuse | Use existing workflow service for review, discussion, approval, due date and audit. |
| Training Mapping | Map SOPs to role, department and required training. |
| Acknowledgments | Employee acknowledges the specific SOP version after training. |
| Manager View | Managers see team training, acknowledgment and overdue items. |
| SOP-to-KPI Mapping | Connect SOPs to measurable KPIs and role scorecards. |
| Audit Findings | Create findings, assign corrective action, due date and status. |
| Dashboards | CEO/Ops see adoption, overdue reviews, pending training, acknowledgment gaps and audit findings. |

Developer / Replit Implementation Brief Build a Process Governance Center for Hire'in Solutions inside the existing HireHR / multi-portal app. Do not create a separate SOP-only workflow engine. Reuse the existing review, discussion, approval, notification, audit, RBAC and ticket/approval patterns already present in the application. Add SOP as a supported workflow entity type. Build SOP library, version control, review routing, discussion, approval, training assignment, employee acknowledgment, SOP-to-KPI mapping and audit finding tracking. Published SOPs must be locked, and revisions must create new versions. CEO/Super Admin must be able to publish after reviewer due dates pass. Managers must see team training and acknowledgment completion. Employees must see only assigned published SOPs and required training.

# 11. How to Make People Follow Without Overwhelming Them

| Risk | Control |
| --- | --- |
| People see SOPs as paperwork | Start every launch with the value: less chaos, fewer rejections, better candidate trust, faster fills. |
| Managers delay review | Use 5-business-day review SLA and no-response/no-objection status. |
| Recruiters ignore documents | Convert SOPs into daily checklists and ATS-required fields. |
| Too many SOPs at once | Launch in waves and role-specific training. |
| No enforcement | Start soft audits by Week 3 and full enforcement after training and acknowledgment. |
| Fear of punishment | Position first 30 days as coaching; repeated gaps move to performance action. |
| Tools misunderstood | Train clear positioning for KleriQ and ProKred as independent SaaS platforms used by Hire'in. |
| No business impact | Tie SOPs to submission quality, interview ratio, start ratio, aging, compliance, margin and candidate feedback. |

# 12. SOP-by-SOP Launch Matrix

| SOP Code | Title | Launch Wave | Training Method | Success Measure |
| --- | --- | --- | --- | --- |
| HIS-SOP-GOV-001 | SOP Governance, Document Control & Change Management | Wave 0 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-REQ-001 | AI-Driven Requirement Synthesis, Hiring Manager Alignment & Execution Brief | Wave 1 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-TA-001 | Requisition Intake, Rate Alignment & Delivery Kickoff | Wave 1 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-TA-002 | Sourcing, Outreach, Candidate Ownership & Consent | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-TA-003 | Screening, Qualification & Submission QC | Wave 1 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-TA-004 | Interview, Offer, Start & Retention Follow-Through | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-HC-001 | Healthcare Credential Packet & Compliance Readiness | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-IT-001 | IT Staffing Delivery, Technical Screening & Submission Governance | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-ENG-001 | Engineering & Professional Services Delivery Standards | Wave 3 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-SALES-001 | Client, MSP/VMS, Rate Governance & Escalation | Wave 1 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-BD-001 | New Client Acquisition, Proposals, RFPs & Client Onboarding | Wave 3 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-MKT-001 | Employer Brand, Digital Marketing & Lead Generation | Wave 3 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-CX-001 | Candidate Experience, Communication SLA & Re-Engagement | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-PLAT-001 | Independent SaaS Platform Usage - KleriQ.ai and ProKred.com | Wave 2 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-LEGAL-001 | Contracts, Data Privacy, EEOC & Immigration Compliance | Wave 4 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-FIN-001 | Invoicing, Contractor Payroll, AR/AP & Margin Governance | Wave 4 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-OPS-001 | Tool Access, Credential Control & Deprovisioning | Wave 1 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-HR-001 | Training, Acknowledgment, Goals & Performance Linkage | Wave 0 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-SOP-AUDIT-001 | KPI Dashboard, Weekly Audit & Monthly Business Review | Wave 0 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-TRAIN-001 | Role-Based Training Curriculum & Certification Plan | Wave 4 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |
| HIS-TPL-001 | Manager Acknowledgment, Audit Checklists & Field Templates | Wave 4 | Role-based micro-training + acknowledgment | Adoption/audit score; role-specific KPI mapping |

# 13. Launch Communication to Team

Suggested Announcement Team, We are launching Hire'in's SOP operating framework in phases. This is not being introduced to create paperwork. The purpose is to reduce staffing chaos, improve requirement understanding, protect candidate trust, improve client communication, strengthen credential and document readiness, and help us fill roles faster with better quality. We will not release everything at once. Each SOP will be introduced with short training, practical examples, checklists and clear expectations. The first phase will focus only on the operating controls that matter most: requirement clarity, rate alignment, submission quality, approved tool usage and communication discipline. Managers will guide their teams through each phase. Employees will be asked to acknowledge only the SOPs relevant to their role after training. The first 30 days will focus on coaching and adoption. After that, SOP adherence will become part of scorecards, audits and performance expectations. Our goal is simple: clearer work, stronger candidates, better client trust and more consistent delivery. - Hire'in Leadership

# 14. Manager Launch Checklist

Attend leadership orientation before launching SOPs to the team.

Review only the SOPs assigned to your department and wave.

Explain the business reason before explaining the process.

Run one live example with the team, not just a slide/training document.

Confirm every impacted employee has completed training and acknowledgment.

Use weekly audits for coaching during the first 30 days.

Escalate real blockers early through the app workflow.

Do not create side processes or unofficial exceptions outside the approved system.

Capture improvement suggestions for Version 1.1 instead of delaying Version 1.0 rollout.

# 15. KPIs to Prove the SOPs Are Valuable

| KPI | Target / Direction | Why It Matters |
| --- | --- | --- |
| Intake completeness score | 90%+ after Wave 1 | Prevents blind sourcing. |
| Submission QC pass rate | 95%+ after Wave 2 | Reduces client rejection and rework. |
| ATS same-day update rate | 90%+ | Improves visibility and manager control. |
| Candidate communication SLA adherence | 90%+ | Improves candidate experience and trust. |
| Credential packet completeness | 95%+ for healthcare submissions | Supports compliance and faster onboarding. |
| ProKred adoption for applicable candidates | Track adoption, not forced usage | Measures candidate-side platform acceptance. |
| Rate/margin exception approvals documented | 100% | Protects profitability. |
| Access removal on exit | Same day | Protects company accounts and data. |
| Training completion | 95%+ by due date | Ensures employees know expectations. |
| Audit findings closed on time | 90%+ | Turns process gaps into action. |

# 16. Source and Standards Alignment

This playbook is aligned with Hire'in internal positioning, healthcare delivery deck themes, current HireHR multi-portal architecture, and selected external staffing/HR/security standards. External standards should be treated as guidance, not legal advice.

| Source / Standard | How It Supports This Playbook |
| --- | --- |
| Hire'in Healthcare Staffing Capability Deck | Supports intake calibration, credential-aware screening, submission QC, MSP/VMS readiness, pipeline visibility and interview-to-start follow-through. |
| HireHR Multi-Portal Architecture | Supports centralized auth, RBAC, audit logs and a shared app foundation for SOP workflow and training. |
| ASA Code of Ethics | Supports ethical staffing, dignity/respect, lawful conduct and qualified placements. |
| ASA Search and Placement Code | Supports candidate confidentiality and client confidentiality. |
| SHRM Policy Acknowledgment Guidance | Supports employee acknowledgment of policies/SOPs after publication and training. |
| NIST Least Privilege AC-6 | Supports role-based access and tool deprovisioning standards. |
| EEOC Selection Procedure Guidance | Supports job-related and consistent selection/screening practices. |

# 17. CEO Decision Needed

Approve the 21-SOP library as the Version 1.0 baseline.

Approve the wave-based rollout instead of one-time mass rollout.

Confirm KleriQ.ai and ProKred.com positioning as independent SaaS platforms used by Hire'in in pilot/design-partner workflows.

Authorize development team to build SOP governance using the existing central workflow service, not a duplicated SOP approval engine.

Set Wave 1 go-live date and first 30-day coaching window.

Require managers to report adoption weekly using the SOP dashboard once built.