Hire'in Solutions

Process Implementation Bible

Manager Review Draft - SOPs, Training, Goals, Audits, and Rollout Controls

Document Code: HIS-IMPL-000 | v1.0 - Manager Review Draft | Prepared: June 22, 2026

| Document Code | HIS-IMPL-000 | Document Title | Process Implementation Bible |
| --- | --- | --- | --- |
| Owner | CEO / Ops | Approver | CEO |
| Audience | Leadership, Managers, Ops, HR, Sales, TA Delivery | Status | v1.0 - Manager Review Draft |
| Effective Date | Upon leadership approval | Review Cycle | Quarterly for first 2 quarters, then semiannual |
| Confidentiality | Internal - Hire'in Solutions only | System of Record | Employee portal / approved shared drive |

# 1. Executive Operating Intent

This manual converts Hire'in SOPs into a working operating system. It is designed for manager review, team training, KPI linkage, weekly audit, and full implementation across Healthcare staffing, IT staffing, Sales, HR, Ops, and Compliance.

Protect candidate and client trust through clear ownership, confidentiality, and controlled access.

Improve delivery speed without sacrificing quality, compliance, or documentation.

Reduce rework by requiring intake calibration, submission readiness, and credential-aware review.

Make performance expectations measurable through scorecards and SOP audit controls.

Create a repeatable operating rhythm that managers can train, inspect, coach, and enforce.

# 2. Hire'in Operating Principles

| Principle | Operating Meaning |
| --- | --- |
| Speed with control | Fast delivery must still meet documentation, rate, candidate consent, and submission quality standards. |
| Quality before volume | Submissions count only when they are qualified, documented, and aligned to client requirements. |
| Confidentiality as a pillar | Candidate, client, rate, credential, and internal process information must be protected. |
| Manager ownership | Every SOP has an owner, evidence requirement, quality gate, and audit cadence. |
| Tool discipline | CEIPAL/ATS, Teams, email, VMS, LinkedIn/RPS, Dice, Indeed, SignalHire, Zoom, KlerHire/ProKred, shared drives, and future tools must be used consistently. |
| No tribal knowledge dependency | Work must be visible in systems, not hidden in personal messages, local files, or informal memory. |

# 3. SOP Library - Clear Titles

| Code | SOP / Control Document Title | Owner | Approver | Primary Audience |
| --- | --- | --- | --- | --- |
| HIS-SOP-GOV-001 | SOP Governance, Document Control & Change Management | CEO / Ops | Leadership | All managers, Ops, HR |
| HIS-SOP-TA-001 | Requisition Intake, Rate Alignment & Delivery Kickoff | TA Delivery Manager | CEO / Sales Director | Recruiters, Leads, AMs, Sales |
| HIS-SOP-TA-002 | Sourcing, Outreach, Candidate Ownership & Consent | TA Delivery Manager | CEO / HR | Recruiters, Leads, AMs |
| HIS-SOP-TA-003 | Screening, Qualification & Submission Quality Control | TA Delivery Manager | CEO / Compliance | Recruiters, Leads, AMs |
| HIS-SOP-TA-004 | Interview, Offer, Start & Retention Follow-Through | TA Delivery Manager | CEO / Sales Director | Recruiters, Leads, AMs, Sales |
| HIS-SOP-HC-001 | Healthcare Credential Packet & Compliance Readiness | Healthcare Manager | CEO / Compliance | Healthcare TA, Ops, Compliance |
| HIS-SOP-IT-001 | IT Staffing Delivery, Technical Screening & Submission Governance | IT Delivery Manager | CEO / Sales Director | IT recruiters, Account Managers |
| HIS-SOP-SALES-001 | Client, MSP/VMS, Rate Governance & Escalation | Sales Director | CEO | Sales, AMs, Delivery Managers |
| HIS-SOP-OPS-001 | Tool Access, Credential Control & Deprovisioning | Operations | CEO / HR | All employees, managers, Ops |
| HIS-SOP-HR-001 | Training, Acknowledgment, Goals & Performance Linkage | HR / Ops | CEO | All employees and managers |
| HIS-SOP-AUDIT-001 | KPI Dashboard, Weekly Audit & Monthly Business Review | Ops / Delivery Leadership | CEO | Managers, Ops, HR, Sales |
| HIS-TRAIN-001 | Role-Based Training Curriculum & Certification Plan | HR / Training Lead | CEO | All employees and managers |
| HIS-TPL-001 | Manager Acknowledgment, Audit Checklists & Field Templates | Ops / HR | CEO | Managers and Ops |

# 4. 90-Day Rollout Roadmap

| Timing | Milestone | Action | Evidence |
| --- | --- | --- | --- |
| Week 1 | Leadership and manager review | Managers mark must-change items; no uncontrolled rewriting. | Redline/comments consolidated by Ops. |
| Week 2 | Final approval and document control | CEO approves v1.0; Ops publishes controlled copies. | SOP index and change log completed. |
| Week 3 | Foundation training | All employees trained on confidentiality, tool discipline, access, ATS hygiene, escalation. | Attendance + acknowledgment captured. |
| Week 4 | TA and healthcare training | Role-based delivery, sourcing, screening, submission QC, credential-aware readiness. | Quiz + work sample certification starts. |
| Week 5 | Sales/MSP/VMS and Ops/HR training | Rate governance, client communication, VMS updates, access control, training records. | Manager certification begins. |
| Week 6 | Soft enforcement | Coaching first; track misses without punitive action unless severe. | Weekly audit scorecard starts. |
| Weeks 7-8 | Controlled enforcement | Repeated misses require written coaching and corrective actions. | Corrective action tracker active. |
| Weeks 9-12 | Full enforcement | SOP compliance linked to goals, scorecards, role reviews, and PIP when required. | MBR includes SOP compliance. |
| End of Month 3 | Effectiveness review | Leadership reviews adoption, bottlenecks, KPI improvements, and policy gaps. | Version 1.1 update decision. |

# 5. Number 10 - SOP Training + Goal Implementation Matrix

This matrix is the master control sheet for converting SOP documents into training, team goals, audit routines, and enforcement dates.

| SOP | Role Impacted | Training Required | Training Type | Quiz | KPI Linked | Audit Owner | Frequency | Evidence | Target | Enforcement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HIS-SOP-GOV-001 | All Managers / Ops / HR | SOP ownership, version control, approval routing, exception handling | Manager orientation | Yes | SOP review completion, change log compliance | Ops | Monthly during rollout | Approved SOP index, change log, acknowledgments | 100% docs controlled | Week 2 |
| HIS-SOP-TA-001 | Recruiters / Leads / AMs / Sales | Requirement intake, must-haves, pay/bill rate alignment, delivery kickoff | Live workshop + role play | Yes | Intake completeness, rate approval, role release readiness | Delivery Manager | Weekly | Intake notes, rate sheet, assignment board | 95%+ complete | Week 6 |
| HIS-SOP-TA-002 | Recruiters / Leads | Sourcing tools, outreach ethics, candidate ownership, consent/RTR | Live workshop | Yes | Candidate ownership logs, duplicate avoidance, outreach quality | Lead Recruiter | Weekly | ATS notes, candidate consent record | 100% consent where required | Week 6 |
| HIS-SOP-TA-003 | Recruiters / Leads / AMs | Screening, qualification, submission checklist, QC gate | Workshop + submission audit | Yes | Submission acceptance rate, rework rate, interview conversion | Lead / AM | Weekly | Submission packet, QC checklist | 95%+ QC pass | Week 6 |
| HIS-SOP-TA-004 | Recruiters / Sales / AMs | Interview scheduling, offer management, start tracking, post-start retention | Scenario training | Yes | Interview show rate, offer-to-start, start retention | AM / Delivery Manager | Weekly | Interview tracker, offer notes, start confirmation | 90%+ show rate | Week 7 |
| HIS-SOP-HC-001 | Healthcare TA / Ops / Compliance | Credential-aware screening, license/cert checks, packet handoff, audit readiness | Compliance lab | Yes | Credential packet completeness, expiration tracking | Healthcare Manager / Ops | Weekly | Credential packet, verification notes | 100% required docs | Week 7 |
| HIS-SOP-IT-001 | IT Recruiters / AMs | IT requirement calibration, technical screening, visa/work auth, submission standards | Functional training | Yes | Submittal quality, interview ratio, margin guardrail | IT Delivery Manager | Weekly | ATS submission notes, tech screen summary | 95%+ complete | Week 7 |
| HIS-SOP-SALES-001 | Sales / AMs / Delivery Managers | Client/MSP/VMS communication, rate governance, SLA, escalation | Manager workshop | Yes | Client cadence, status update timeliness, margin review | Sales Director | Weekly | Client update log, VMS status, escalation log | 95%+ status accuracy | Week 7 |
| HIS-SOP-OPS-001 | All employees / Ops / Managers | Tool request, access approval, least privilege, password reset, removal | Ops briefing | Yes | Access request approval, deprovisioning completion | Ops | Weekly | Access register, approval email/ticket | 100% approval before access | Week 5 |
| HIS-SOP-HR-001 | HR / Managers / All Employees | Training records, acknowledgments, role scorecards, coaching/PIP linkage | HR manager training | Yes | Training completion, acknowledgment, coaching records | HR / Ops | Weekly rollout; monthly after | LMS/training record, signed acknowledgment | 100% completion | Week 8 |
| HIS-SOP-AUDIT-001 | Managers / Ops / CEO | Weekly audit, KPI dashboard, monthly business review, corrective actions | Leadership workshop | Yes | Audit score, corrective action closure, KPI adoption | Ops / CEO | Weekly + Monthly | Audit sheet, scorecard, MBR deck | 90%+ audit score | Week 8 |
| HIS-TRAIN-001 | All teams | Role-based curriculum, certification, quizzes, live work sample checks | Training program | Yes | Certification completion and behavior adoption | HR / Training Lead | Weekly during rollout | Attendance, quiz score, certification tracker | 90% quiz pass | Week 4 |
| HIS-TPL-001 | Managers / Ops | Use of standardized templates and checklists | Manager walkthrough | No | Template usage, consistent documentation | Ops | Weekly | Completed forms/checklists | 95% usage | Week 6 |

# 6. Role-Based Scorecard Linkage

| Role | Primary Goal | Monthly / Weekly Standard |
| --- | --- | --- |
| Associate Recruiter | Activity + process adoption | 40-60 screened candidates/month; 12-18 qualified submissions/month; 100% ATS notes same day; 0 unauthorized submissions |
| Recruiter | Delivery production | 60-80 screened/month; 18-25 qualified submissions/month; 2-4 interviews/month; 95% submission QC pass |
| Senior Recruiter | Conversion + ownership | 80-100 screened/month; 25-35 qualified submissions/month; 4-6 interviews/month; 1+ start target; coaches juniors when assigned |
| Lead Recruiter | Quality + team control | Weekly QC, aging review, two coaching notes per recruiter/week, 95% submission quality, escalation within 24 hours |
| Account Manager | Client + margin control | 100% requirement intake completeness; VMS status accuracy 95%+; rate/margin approval captured; weekly client updates |
| Delivery Manager | Execution system | Weekly team forecast, KPI review, audit closure, role prioritization, submission-to-interview improvement |
| Ops / HR | Control + records | 100% access approvals, training acknowledgments, exit deprovisioning same day, audit records retained |

# 7. Audit and Business Review Rhythm

| Cadence | Performed By | What Is Reviewed | Accountable Owner | Output |
| --- | --- | --- | --- | --- |
| Daily | Recruiter | ATS notes, priority role activity, candidate follow-ups | Team Lead | End-of-day check |
| Weekly | Lead / AM | Submission QC, aging roles, credential readiness, VMS accuracy | Delivery Manager | Friday scorecard |
| Biweekly during rollout | Ops / HR | Training completion, access compliance, acknowledgments | CEO / Ops | Rollout dashboard |
| Monthly | Leadership | Starts, margin, fill ratio, client feedback, audit score, corrective actions | CEO | Monthly Business Review |
| Quarterly | Leadership + HR | SOP effectiveness, policy gaps, scorecard adjustment | CEO | Version update or sign-off |

# 8. Manager Implementation Rules

Managers must train the SOP before enforcing it, except for confidentiality, data security, fraud, or severe compliance issues.

Managers must document coaching before moving to PIP unless the issue is severe or intentional.

A recruiter cannot be judged only by submission volume; quality, documentation, candidate handling, and conversion must be part of performance.

Client or VMS submissions should not go out unless the role intake, rate/pay alignment, candidate consent, and submission QC are complete.

Healthcare submissions require credential-aware review before client submission where the role requires license/certification documentation.

Access must follow least privilege and must be removed immediately upon exit, role change, or business need ending.

# 9. Training Design

| Training Track | Audience | Content | Duration | Certification Evidence |
| --- | --- | --- | --- | --- |
| Foundation | All employees | Confidentiality, data handling, Teams/email discipline, ATS hygiene, access rules | 60 min | Attendance + acknowledgment |
| TA Delivery | Recruiters, Leads, AMs | Intake, sourcing, screening, submission QC, interview/start follow-up | 2 x 90 min | Quiz + live submission audit |
| Healthcare Compliance | Healthcare TA, Ops | License/cert checks, credential packet control, expiry awareness, onboarding readiness | 2 x 90 min | Credential packet work sample |
| IT Staffing | IT TA, AMs | Technical qualification, work authorization, rate/margin guardrails, client submission notes | 90 min | Tech screen summary review |
| Sales/MSP/VMS | Sales, AMs, Delivery Managers | Client communication, VMS status, rate governance, escalation, weekly reporting | 90 min | Scenario review |
| Manager Certification | Leads, AMs, Managers | How to audit, coach, reject weak submissions, escalate, and enforce | 2 hours | Manager certification checklist |

# 10. Final Go-Live Gate

| Gate | Completion Standard | Owner |
| --- | --- | --- |
| SOP approval | All priority SOPs approved and version controlled | CEO / Ops |
| Training completion | 100% of active staff trained or scheduled with documented exception | HR / Ops |
| Acknowledgment | All employees sign SOP acknowledgment | HR |
| Manager certification | Leads/AMs/managers complete audit/coaching certification | CEO / Ops |
| System readiness | ATS fields, shared folders, templates, access register, audit sheets ready | Ops |
| Audit launch | Weekly SOP audit begins | Ops / Delivery Leadership |

# Reference Basis

These SOPs are designed as internal operating controls. They are not legal advice and should be reviewed by counsel/HR where required before final publication.

| Reference | URL |
| --- | --- |
| Hire'in eHealthcare / Staffing positioning | https://hire-in.com/ehealthcare-staffing |
| Hire'in IT staffing positioning | https://hire-in.com/it-staffing |
| ASA Code of Ethics | https://americanstaffing.net/asa/asa-code-of-ethics/ |
| ASA Search & Placement Code of Ethics | https://americanstaffing.net/asa/asa-code-of-ethics/search-and-placement-code-of-ethics/ |
| NIST Least Privilege Glossary | https://csrc.nist.gov/glossary/term/least_privilege |
| The Joint Commission HCSS Certification | https://www.jointcommission.org/en-us/certification/health-care-staffing |
| Joint Commission HCSS-7 Personnel File Completeness | https://manual.jointcommission.org/releases/HCSS2026B/MIF1358.html |
| EEOC | https://www.eeoc.gov/ |
| Kirkpatrick Model | https://www.kirkpatrickpartners.com/the-kirkpatrick-model/ |